## Example
RACI Chart (Roles and Responsibilities Matrix)
Process Name / Description: | Bad-Teacher-Jokes App: Social Networks for jokes
Created On: | 2017-09-18 | Revision: | 2017-10-30
Created by: | Jeroen Loosli (Investor), Nico Lutz (Proj.Mgr), Marc Vollenweider (Coder 1), Patrick Wissiak (Coder 2), Vithun Vamathevan (Coder 3), Gabriel Meier (Coder 4), Alexandre Maurer (Coder 5)
Tasks | Investor | Proj. Mgr | Coder 1 | Coder 2 | Coder 3 | Coder 4 | Coder 5
Identify investors | C | - | - | - | - | R | '-
Arrange for investor visits | I | R | - | - | - | - | -
Arrange for project meetings | - | R | I | I | I | I | I
Arrange for project management software | - | R | C | C | I | I | I
Review input of stakeholders and… | A | I | I | - | - | R | '-
Protocol | I | I | - | - | - | - | R
Communicate project to promote….. | I | I | R | I | I | I | I
Provide security strategies the coders crew by June 15 | I | - | A | R | R | I | I
Oversee the project during …., ensure it is completed on time | A | I | I | - | - | R | '-
R = Responsible, A = Accountable, C = Consulted, I = Informed